## Slide 1: BD GSSP
WORK PRODUCTS
Setting up the product in the GSSP application and Testing:
  Configure Illustrations – Insured Details, Product Info, Coverages, Riders and Quote Summary.
  Configure Applications – Beneficiary, Insured Details, Underwriting Questions, Payments, Application Summary
  Setup Illustration and Application PDFs
  Testing in SIT and QA environments
Working on the following CRs :
  Address Issue – Introduce ‘Other’ option for the user when the desired entry is not found in the dropdown.
  Bonus Rate Change – Change the bonus rate table and test the changes.
  FAQ content – Introduce FAQ section in the GSSP application and add ‘Helo Bima’ content.
CURRENT STATUS (AS OF Nov 8, 2022)
New Product Testing in SIT (Capgemini)
New Product Testing in UAT (Bangladesh Business Team)
New Product Defect Fixing and Defect Retesting (Capgemini)
Fix complete for the CRs – Address, Bonus Rate and FAQ. Testing in Progress.
GOOD PRACTICES:
We discussed issues frequently so they could be resolved
Followed Agile Practices – User story creations, Sprints, Daily Stand Ups etc..
Business engagement is frequent and collaborative, increasing the chance of Successful implementation.
All changes went through the change control process
CHALLENGES AND OVERCOMES
Team faced challenges during deployments in the initial phases which lead to slight delay in testing the product - Team spent extra time to learn the deployment process from the existing team and made sure the delay is moderate
Two new resources were added after the transition – KT plan was created for the new resources, and it was followed diligently and made sure it did not impact the project schedules.
Bangladesh Global Sales and Support Platform (BD GSSP)
Plan to launch new product (My Child’s Education Protection Plan – MCEPP) into the market sometime in the month of November.
Planning to move high priority CRs in the next release (Nov 14) – Address Issue, Bonus Rates Change and Introduce FAQ content.
FUTURE PLANS
Team will be working on existing prioritized CRs (currently there are 20 CRs pending) and any new Product Launches in future
GSSP APPLICATION
High Level Workflow/Data flow (GSSP application)
User Journey (GSSP Application)